| Project Title: | Promoting quality education through progressive domestic resource mobilization |
| --- | --- |
| Name of Country: | FAYA Nepal |
| Reporting period (Year/Quarter) | Final Report 2015 August to 2017 December |

## Summary of progress (1/2 page)

FAYA Nepal implemented the “Promoting Quality Education through Domestic Resource Mobilization” project in partnership with ActionAid Nepal, with financial support from NORAD. The project was carried out from August 1, 2015, to December 31, 2017. During this period, the program primarily focused on three key areas: improving learning achievement, strengthening school governance, and raising awareness through tax power campaigning.

To enhance learning outcomes, the project undertook several initiatives such as training on child-centered learning approaches, providing teaching and learning materials, and improving classroom management. Additional activities included forming and regularly engaging child clubs, organizing extracurricular activities, establishing Education Concern Groups (ECGs) to support school-level initiatives, and activating Gender Focal Teachers and Gender Equality Networks (GEN). The project also introduced orientation and follow-up on the Continuous Assessment System (CAS) to ensure its ongoing implementation in schools.

In the initial phase of the project, child clubs were formed and mobilized through meetings and activities like sanitation campaigns. ECGs were also established to conduct regular monitoring visits and support school development efforts. These groups played a crucial role in organizing integrated meetings that brought together teachers, students, School Management Committees (SMCs), and Parent-Teacher Associations (PTAs) to collaboratively address school-level issues and develop contextual action plans.

Child club materials were distributed to 15 clubs, including resources for both mental and physical development, such as life cycle charts, storybooks, globes, and sports kits. With support from focal teachers, each club developed annual action plans to guide their activities.

Project field staff also participated in resource center-level meetings with headteachers, where they advocated for the assignment of Gender Focal Persons. Discussions included references to the “Gunaso Sunuwai Nirdeshika” (Grievance Hearing Guidelines). Although the need for focal teachers had been raised previously, many schools had not yet made appointments. Following these meetings, all 30 schools involved in the project successfully designated Gender Focal Teachers.

FAYA Nepal organized orientations on government provisions related to girls’ education in all 30 project schools. These sessions included the participation of school supervisors, Resource Persons (RPs), and various school stakeholders. Participants were informed about the government’s support mechanisms for girls' education and expressed their commitment to aligning school efforts with these policies.

To understand the flow of education financing, the project conducted a comprehensive mapping study to analyze funding sources from government, non-governmental entities, and parents, along with expenditure patterns. Based on the findings from this study and the Citizen Education Report (CER), three radio jingles were developed to raise public awareness on education financing and local resource mobilization. These jingles were broadcast throughout 2017 via FM radio to disseminate messages on quality education.

The project also established three community libraries—one each in Urma, Phulwari, and Hasuliya. The concept for these libraries was developed to enhance learning environments and promote parental involvement in schools. The libraries serve both students and the wider community as spaces for learning and knowledge sharing.

Additionally, the project facilitated discussions on government provisions for girls’ education in all project schools. These discussions involved Education Concern Groups (ECGs), Mothers’ Groups, and girl students to promote understanding and engagement.

Participatory Rights in School (PRS) interactions were held in the three clusters (Urma, Phulwari, and Hasuliya), bringing together teachers, ECG members, Mothers’ Groups, SMCs, PTAs, and child club members. Participants engaged in discussions around the "10 Rights in School" framework, gaining clarity on their roles and responsibilities.

Two-day PRS trainings were also organized in all three clusters for ECGs, Mothers’ Groups, and child clubs. The first day focused on theoretical discussions, while the second involved field visits to schools. During these visits, participants gathered information, interviewed community members, and interacted with students and teachers, helping them better understand the ground realities of school environments.

The formation and activation of child clubs led to noticeable improvements in student behavior and academic performance. Prior to the child clubs, students were often hesitant to engage with teachers and only participated in extracurricular activities when forced. Now, students are actively organizing and participating in events on their own initiative, demonstrating leadership and responsibility. They also represented their schools in cluster-level events and achieved various recognitions.

Parental involvement in school affairs increased significantly following the mobilization of ECGs. These groups began conducting regular monthly or quarterly meetings, planning how to support and monitor schools effectively. ECG members also held teachers accountable for their attendance and punctuality. Furthermore, integrated meetings were organized, involving SMCs, PTAs, ECGs, teachers, and students to collectively identify local challenges and create action plans for school improvement.

FAYA Nepal organized public hearing programs in three clusters based on the findings of the Public Education Financing Mapping research. These hearings were attended by newly elected local representatives and key school stakeholders. The forums served as a platform to discuss education financing, identify gaps, and promote accountability among duty-bearers.

To ensure every school-aged child in the project areas was enrolled, enrolment campaigns were conducted across all 30 project schools. These campaigns were carried out in collaboration with teachers, students, School Management Committees (SMCs), Parent-Teacher Associations (PTAs), and Education Concern Groups (ECGs). Door-to-door visits were conducted in school catchment areas to identify out-of-school children and school dropouts. During these visits, parents were informed about government-provided educational facilities and the improvements in school learning environments, encouraging them to enroll their children.

To strengthen the capacity of ECG members on issues of tax and resource mobilization, a two-day training on “Tax Power” was organized. The training aimed to build awareness about different types of taxes and promote the concept of tax justice. Following the training, participants developed action plans and carried out tax awareness campaigns in their respective communities.

Child clubs were also restructured during the project period due to the transition of student members to higher grades or other schools. New members were inducted to ensure continuity. The reformed clubs were actively engaged in planning and conducting awareness activities, including those related to tax justice.

On Children's Day (29th Bhadra), a Girls' Conference was organized in Dhangadhi at the Nepal Chamber of Commerce Hall. The event began with a large rally from Campus Chowk to the conference venue, where participants wore card-paper caps and carried placards with slogans that drew attention from the public. The formal session was chaired by child club member Preeti Sunar, with the Head of the Women and Children Office of Kailali as the chief guest. Presentations were made by School Inspector Pratap Singh Dhami on government provisions for girls' education, and by journalist Bhim Chaudhary on the status of girls in schools. The event concluded with a workshop and the adoption of the "Seven Kailali Declarations" in support of girls' education.

A district-level PRS (Participatory Rights in School) interaction was also conducted with ward members and the Mayor of Dhangadhi Sub-Metropolitan City. This session, facilitated by FAYA Chairperson Sher Bahadur Basnet, introduced the participants to the "10 Rights in Education" and highlighted their roles in policymaking and ensuring the implementation of these rights at the local school level.

Education Concern Group (ECG) members led tax power campaigns at the local level, organizing various awareness-raising activities within their communities. These included street dramas, rallies, interactive sessions, and orientation programs. These grassroots initiatives proved highly effective in educating local residents about taxation, its importance, and its role in development.

District Project Advisory Committee (DPAC) meetings were held quarterly, while DPAC field visits took place twice a year. These platforms provided opportunities for stakeholders to visit project sites, review ongoing activities, and engage in meaningful discussions. Participants offered valuable feedback and recommendations to enhance project implementation.

A tax power interaction program was conducted with local leaders across Kailali district. This initiative aimed to raise awareness among local representatives on tax collection and emphasize the importance of allocating public funds to the most pressing needs of the community.

School stakeholders also received orientation on the social audit process, led by school supervisors and Resource Persons (RPs). As a result, all project schools now conduct social audits annually, following proper guidelines and procedures. Furthermore, schools were oriented on the preparation and timely updating of School Improvement Plans (SIPs). Before the project, most schools did not regularly update their SIPs. With project support, this process became systematic and participatory, involving input from relevant stakeholders. Notably, Garima Basic School and Bandevi Basic School in Hasuliya were among the first to develop and submit their SIPs to the District Education Office (DEO).

Multiple awareness activities on tax justice and transparency were also carried out to ensure that students, parents, teachers, and committee members understand the tax system. Following their participation in orientations, trainings, interactions, and campaigns, stakeholders gained knowledge about tax collection, allocation, and its fair utilization. They are now able to explain these processes to others in their communities.

Finally, a district-level learning and sharing event was organized, bringing together all key stakeholders to reflect on the project’s achievements, challenges, and lessons learned.

## 2. Progress against outputs (4 pages)

| # Please report against the activities planned under each output for the current reporting period. Under the column ‘activity report’ please provide brief details covering: - The type of activity (e.g. training workshop, research, advocacy etc.) conducted - The purpose of the activity - The key beneficiaries involved, or stakeholders targeted by the activity and why. Please provide gender (and where appropriate, age) disaggregated figures - The Results of the activity - Any next steps planned Please add as many lines as you need against each milestone. If implementation has deviated from the original plan by 3 months or more, please list any consequences and plans to address these. |  |  |  |
| --- | --- | --- | --- |
| Output 1 Children, especially girls, parents, community members and local civil society have a strong role in ensuring that local education services are of high quality, increase access for girls and are adequately funded by government through fair taxation. |  |  |  |
| Milestone | Activity report (including any deviations from original plan by 3 months or more) | Planned completion date | Actual completion date |
| M1 Participatory training for local communities living in poverty and local interest groups on rights to education, taxation and financing of education, budget tracking of education resources and other techniques to monitor quality public education e.g. social audits, Community score cards | Capacity building for partners on promoting rights in school to ensure quality education Capacity building for staff/partner on Tax campaign Orientation of SMc, PTA and teachers and children on promoting rights in school Training on Child Centered Learning (CCL) to teachers Orientation on Child Centered Learning (CCL) approach to HT, SMC and PTA - Four rounds of orientation on the Child-Centered Learning (CCL) process were conducted for school stakeholders to support the effective implementation of grade teaching in schools. - The first round of orientation was held in Dhangadhi with 60 participants, followed by sessions in Urma (54 participants), Hasuliya (54 participants), and Phulwari (63 participants). - A total of 231 stakeholders attended the orientations, comprising 86 females and 145 males. Participants included members of School Management Committees (SMCs), Parent-Teacher Associations (PTAs), Head Teachers, and Education Concern Group (ECG) members. - The key outcome of these orientations was the stakeholders’ commitment to transition to floor-sitting classroom arrangements and to adopt grade teaching methods, particularly in grades one to three. Participants gained a clear understanding of the child-centered learning approach and expressed readiness to monitor its implementation at the local level. Training on Child Centered Learning (CCL) Process to teachers - Three rounds of Child-Centered Learning (CCL) training were conducted for teachers from project schools in Dhangadhi. - A total of 86 teachers (42 females and 44 male) from 30 project schools participated in the training sessions. - The training significantly enhanced the professional competencies of teachers, resulting in noticeable improvements in their attitudes and classroom behavior. It helped create a non-threatening, child-friendly learning environment, fostering stronger relationships between teachers, students, and parents. - Following the training, several students from private schools enrolled in public schools implementing grade teaching. They were drawn by the engaging and interactive learning approaches such as singing child-friendly songs, using educational games, written cards, dice-based learning activities, and dancing. - A teacher from Rastriya Lower Secondary School, Urma, shared that since implementing grade teaching, students have become more curious, frequently asking questions, engaging in peer interactions, and actively participating in classroom activities. CCL learning Sharing workshop (refresher) - To support learning exchange and refresh understanding of the CCL (Child-Centred Learning) process, two rounds of refresher training were conducted in April. - A workshop was also held in Dhangadhi to assess the classroom implementation of CCL, identify challenges faced, and provide clarity on specific tools and practices. - The first round of refresher training was held from April 5th to 7th, and the second from April 8th to 10th, 2017. A total of 30 teachers from project schools participated. - Altogether, 82 teachers attended the training. The first round included 42 participants (26 female and 16 male), and the second round had 40 participants (24 female and 16 male). - The training sessions took place at Nayaram Hotel in Dhangadhi. - Both rounds were facilitated by Rajendra Pokhrel, who had also facilitated the training the previous year. - At the beginning of the sessions, the facilitator collected reflections from teachers on their past experiences and their expectations for the three-day training. - The training addressed difficulties teachers had faced in implementing CCL in their classrooms. Teachers also shared their experiences, which helped others learn practical solutions. - Challenges such as forgotten techniques and unclear concepts were revisited, with additional input and strategies provided. - Teachers expressed their satisfaction, noting that receiving the refresher at the start of the academic session boosted their confidence and preparedness for implementation. - On the final day, participants engaged in micro-teaching sessions to practice and demonstrate their learning. Support for teaching-learning materials to schools Supports for teaching-learning materials to schools - Following the completion of the CCL training, teaching and learning materials were provided to 30 project schools. These materials supported Grades 1 to 3 across a total of 90 classrooms. - The materials included items such as numbered dice, Kutt paper, meta cards, newspapers, cardboard paper, crayons, and more. - These resources were used to create various learning aids, support interactive activities like dice games, and encourage creativity through drawing. - After the distribution of materials, classrooms became more engaging, with many learning aids produced and displayed on the walls. This allowed students to continue learning independently, even in the absence of a teacher. - As a result of the improved classroom environment, many students from private schools were inspired to transfer and enroll in the project schools. Orientation to teachers and head teachers on Continuous Assessment System (CAS) Orientation to teachers and head teachers on Continuous Assessment System (CAS) - Although the government had mandated Continuous Assessment System (CAS) in public schools, many schools struggled to implement it due to confusion about the marking system and assessment procedures. - To address this, the project organized a one-day cluster-level orientation on CAS. The sessions were held on October 23, 2016, in Phulwari; October 24 in Hasuliya; and October 25 in Urma. - The orientations were led by the School Inspector from the Kailali District Education Office, with support from Resource Persons (RPs). - A total of 96 teachers (34 female and 62 male) from 30 project schools participated in the sessions. - The orientation focused on key aspects of CAS, including its introduction, objectives, importance, tools and processes, common challenges and solutions, evaluation methods, and relevant government policies and curriculum links. - As a result of the orientation, teachers began to consistently implement continuous assessment in line with government guidelines. | February 2017 April 2017 | February 2017 April 2017 |
| M2 Creation of evidence based on quality and cost of local education in target areas through participatory research with community members. | Community CRRP Conducted - The Community CRRP (Community Reflection and Review Process) served to validate the project's interventions with key stakeholders. - To strengthen community engagement and foster a sense of ownership toward community schools, CRRP events were conducted in Urma (June), and in Hasuliya and Phulwari (December). - These events saw active participation from various community groups including Child Clubs, Early Childhood Groups (ECG), School Management Committees (SMC), Parent-Teacher Associations (PTA), Mothers' Groups, and teachers. In Urma, 36 individuals participated (21 male and 15 female); in Hasuliya, 29 participants (18 male and 11 female); and in Phulwari, 36 participants (20 male and 16 female). - The purpose of the Community CRRP was to help achieve the project's intended outcomes by raising awareness among community members about the interventions, challenges faced, and progress made. - Activities carried out from January to June 2017 were shared, including achievements, challenges, and best practices. - Following the presentations, participants engaged in group discussions and activities to identify effective practices and areas needing further improvement, which were then shared by the community members. Producing a Citizen's Education Report (CER) at national level Capacity building on PRS to partners - A capacity building training on PRS (Participatory Rural Appraisal/Survey) was conducted in Dhangadhi. - Participants included 11 individuals from Doti and 11 from Kailali, comprising project team members and enumerators responsible for data collection. - The training, held from May 10 to 14, 2016, focused on PRS and baseline survey methodologies, targeting all six data collectors (3 male and 3 female) and four project staff. - The training aimed to develop a clear understanding among participants about PRS covering what to study in the field, identifying key stakeholders, who to consult during the process, and how to gather necessary information effectively. - Data collection procedures were also discussed in detail, and participants took part in simulation exercises. - Following the training, participants visited project schools to collect field data, gaining practical experience. They then regrouped to reflect on the process and discuss potential challenges they might encounter in real-life scenarios. Participatory Assessment of Target Schools (PRS) - Following the PRS training, the assessment process was initiated in the 15 targeted schools. - Six enumerators (3 male and 3 female) were mobilized for the data collection. - The PRS collection involved school-level assessments, focus group discussions (FGDs) with teachers, students, and School Management Committee (SMC) members on various indicators and school facilities, as well as interviews with District Education Office (DEO) representatives and civil society members to gather their perspectives on community schools. Producing Citizen's Education Report at local and district level - An orientation was conducted for enumerators on the CER (Community Education Report) process, including data collection methods and target groups. - Based on the field data collected, a consultant prepared 16 CER reports. - Once the reports were finalized, the key findings were shared at the district level in the presence of Head Teachers and SMC Chairs from the 15 target schools, along with representatives from relevant district-level agencies. - During the sharing event, participants acknowledged that the reports accurately reflected the current situation of community schools. Key recommendations from the discussion included: - Although sufficient physical infrastructure exists, it is poorly managed and underutilized; immediate action is needed to address this. - The government must ensure adequate teacher allocation and necessary resources to create a child-friendly learning environment; otherwise, schools may resort to collecting fees from students under various pretexts. - Monitoring and supervision from the District Education Office (DEO) are currently limited and should be conducted more regularly. - Some participants proposed that there should be a government provision requiring teachers and education personnel to enroll their own children in the schools where they work, to increase accountability and trust in public education. Shared findings of CER Report: - CER (Community Education Report) documents were prepared for 15 project schools, along with a consolidated district-level report based on the findings from these schools. - After the reports were completed, a validation meeting was organized to present and discuss the findings with district-level stakeholders and representatives from the respective schools. - A total of 46 participants attended the sharing meeting, including SMC Chairpersons and Head Teachers from the 15 schools, DPAC members, DEO officials, representatives from the NGO Federation, and other government and non-government organizations working in the education sector. - The findings were presented by Tekendra Deuba, the consultant responsible for compiling the reports. - Participants appreciated the accuracy of the reports, stating that they reflected the true situation of public education. Key points raised included the availability of physical infrastructure that is poorly managed, insufficient monitoring from the DEO, and the urgent need for government support to create more child-friendly school environments. Finalized Community Score Card in 15 Schools: - After completing and sharing the CER reports for 15 schools, the next step was to implement the Community Score Card (CSC) process in the remaining 15 schools. - To facilitate this, two facilitators were oriented on the CSC concept, its process, key indicators, and reporting format. - The CSC focused primarily on 10 key rights, assessed through 18 indicators. During the sessions, facilitators led discussions on each right, and participants rated their school's performance on a scale from 1 to 5 based on their local context and perceptions. - The CSC activities were completed in December, and the final report was submitted accordingly. - The process was conducted with active participation from School Management Committees (SMC), Parent-Teacher Associations (PTA), Early Childhood Groups (ECG), teachers, students, and other relevant stakeholders. A total of 584 stakeholders took part across 15 schools, including 283 females and 301 males. - As a result, school stakeholders gained a better understanding of the 10 rights and the current situation in their respective schools. Lesson Learning and Sharing Workshop Conducted Learning Sharing workshop at District level - A one-day project learning and sharing event was organized at Hotel Rubus on December 28, 2017. - The event was held in the presence of key stakeholders and local leaders, where project progress was presented, and participant feedback was collected. - A total of 62 stakeholders attended the workshop, including 23 females and 39 males. - The program began with opening remarks from PPC Dhanpati Dhungel, followed by a welcome address from FAYA Program Director Dharma Raj Pathak. - Project Coordinator Mukesh Pant then presented an overview of the project's activities, impacts, and the challenges encountered during implementation. - Participants expressed that they had gained valuable insights and found the interventions helpful in their work within schools and communities. - Local leaders also acknowledged the relevance of the project, stating that the learnings would be beneficial in shaping future policies and guiding their ongoing efforts. Public Education Finance Mapping: research Public Education Finance Mapping Exercise: orientation - An orientation on Public Education Financing Mapping Research was held on July 4, 2016, at Dinesh Cottage, Dhangadhi. - A total of 40 participants attended the session, including 9 females and 31 males, comprising members of the Education Concern Group and master's level students involved in the research. - For the study, 20 schools were randomly selected from the 30 project schools. - The orientation included a PowerPoint presentation, Q&A sessions, practical exercises, group work, and participant presentations. - The session focused on mapping the financing of community schools and equipped participants with the knowledge and skills needed for research, data collection, and compilation. - Following the orientation, the research report was finalized and published, incorporating revisions and additional information gathered during the process. Public Education Finance Mapping: research Orientation on Public Education Financing Mapping Exercise - To understand the existing financing mechanisms and the flow of funds in community schools, a research study was initiated under the project. - An orientation was conducted for 11 researchers, most of whom are bachelor's and master's level students, with some currently working on their theses. - Along with the researchers, 20 members from the Education Concern Group also participated to support data collection at the field level. - The orientation began with an overview of the NORAD project, followed by sessions on tax justice, research methodology, and practical exercises. - The full-day orientation was jointly facilitated by the ActionAid team, FAYA Nepal, and lead researcher Bhawan Singh Chalaune. - Participants gained a clear understanding of the data collection process, including identifying appropriate respondents for the research. - Bhawan Singh Chalaune led the research, developing the questionnaire and FGD (Focus Group Discussion) tools used for information gathering. - A separate orientation was held for 10 researchers specifically to explain the research process, questionnaire design, survey format, and FGD methodology. - The research covered 20 project schools—10 from Phulwari, 5 from Hasuliya, and 5 from Urma. In each school, one FGD was conducted, a survey form was completed, and interviews were held with both the Head Teacher and the SMC Chairperson. - The researchers compiled the necessary data for report writing. Some have already submitted their findings to the lead researcher, while others are in the process of finalizing their information. - The report reflects the current educational status in the district, including dropout rates, learning achievement, student-teacher ratios, and parents' perceptions of community schools. Exercise - Following the orientation, data collection began with 10 researchers using the developed data collection tools. - Various formats were used to gather information, including questionnaires for Head Teachers and SMC members, school survey forms, and FGD (Focus Group Discussion) guides. - Based on the collected data, lead researcher Bhawan Singh Chalaune compiled and produced the Education Financing Mechanism (EFM) research report. - A sharing workshop was organized to present the findings, with participation from 54 stakeholders, including SMC Chairpersons and Head Teachers from the 20 schools, DPAC members, DEO officials, NGO Federation representatives, and members of other governmental and non-governmental organizations. Among the participants were 9 females and 45 males. - During the workshop, participants offered several key recommendations: - The report was fact-based and accurately reflected the current financing situation in community schools. - Although physical infrastructure exists, it has not been properly managed or utilized, this should be a priority. - Well-managed schools should be rewarded to encourage better practices. - Parental accountability and engagement in school resource mobilization need to be strengthened. - Existing resources must be used efficiently and effectively. - The lack of properly maintained toilet facilities contributes to increasing dropout rates. - Empowering local communities and improving coordination can support better resource mobilization for schools. - Teacher capacity and pedagogical approaches must be improved, with a shift toward child-centered teaching methods. Conducted FGD with School Stakeholders. - As part of the Public Education Financing Mapping data collection, Focus Group Discussions (FGDs) were conducted in 20 project schools. - In 6 to 7 of these FGDs, the FAYA focal person, lead researcher, and Project Coordinator (PC) were present to guide and support the researchers in facilitating the discussions effectively. - On average, each FGD had around 12 participants, including 2 students, the SMC Chairperson, PTA Chairperson, an ECG member, the Head Teacher, a female teacher, a guardian, and other community representatives. - Each discussion lasted approximately 2 to 3 hours and focused on several key topics: - Community involvement in school activities - School budget allocation and sources - Number of budget headings under which schools receive funds - Perceptions and characteristics of a model school - The role of SMC, PTA, and guardians in developing such model schools in their communities. - Community members actively participated and openly shared their views, ideas, and experiences during the discussions. Conducted Dream school interaction within presence of school stakeholders. - Dream School interaction programs were conducted in all three project areas Urma, Hasuliya, and Phulwari. - The interactions were led by FAYA Chairperson Sher Bahadur Basnet, with the presence of PPC Dhanpati Dhungel, Project Coordinator Mukesh Pant, and lead researcher Bhawan Singh Chalaune. - Participation details were as follows: - Urma: 36 participants (23 males, 11 females, and 2 students) - Hasuliya: 44 participants (28 males and 16 females) - Phulwari: 51 participants (38 males and 13 females) - The interaction sessions focused on key topics such as: - Investment in community schools and how funds are spent - Household spending by guardians on their children’s education annually - Gaps between school and community - Reasons for declining student enrollment - Community vision of an ideal “Dream School” - Self-assessment of local schools against the 10 rights of students through a participatory scoring process - During the discussions, parents became more aware of their annual investment per child, which averaged around NPR 20,000. This included expenses for school uniforms, stationery, tuition fees, exam fees, transportation, snacks, and extra classes. Shared Findings of EFM Research: - As planned under the project, a research study on public education financing mapping was successfully conducted, led by Bhawan Singh Chalaune, a lecturer at Kailali Multiple Campus. - The researcher completed the Education Financing Mapping (EFM) report, and to validate the findings and gather feedback from relevant stakeholders, a one-day findings-sharing workshop was organized at Hotel Devotee, Dhangadhi. - The workshop was attended by 54 stakeholders, including SMC chairpersons and head teachers from the 20 selected schools, DPAC members, DEO officials, representatives from the NGO Federation, and other government and non-government organizations. Among the participants, 9 were female and 45 were male. - Bhawan Singh Chalaune presented the key findings of the report during the session. - Following the presentation, participants provided feedback emphasizing the need to strengthen parental accountability, enhance teachers’ capacity, and mobilize local communities to generate school resources. - The workshop helped participants better understand the status of education financing and how resources are being utilized in community schools. Broadcasted the findings of EFM through FM Radio. - As part of our plan, we aimed to produce and broadcast radio jingles throughout the year based on key findings from the Education Financing Mapping research to disseminate important messages. - Accordingly, three radio jingles were developed and finalized in consultation with AAN/WRC and the District Education Office. - Once the messages were approved, we collaborated with Dhangadhi FM, which produced the jingles using the finalized scripts. These were again reviewed and endorsed by the AAN/WRC team. - We then signed an agreement with Dhangadhi FM to broadcast the jingles regularly throughout the year. - The jingles focused on promoting quality education, mobilizing local resources, tax awareness, and highlighting the current situation of community schools. PRS Baseline, midterm, final evaluation, Producing CER of Schools and District Conducted PRS Orientation - PRS orientation sessions were conducted across three clusters: Urma, Phulwari, and Hasuliya. - On March 25, 2017, the session in Phulwari had 54 participants (36 male and 18 female). On March 26 in Hasuliya, 42 participants attended (26 male and 16 female). On March 27 in Urma, there were 58 participants (32 male and 26 female). - The participants included representatives from SMC, PTA, ECG, child clubs, and mothers’ groups. - The orientation covered topics such as rights and basic needs, the definition of education and literacy, an overview of the 10 educational rights, and an introduction to tax power. - Participants gained a clear understanding of the differences between rights and basic needs, and between literacy and education. They recognized the importance of the 10 rights in supporting children’s learning and committed to promoting them in schools. - They also understood the connection between taxation and education, and how local resource mobilization could contribute to improving the quality of education. Conducted PRS Training - A two-day PRS training was conducted for members of the Education Concern Group (ECG), mothers' groups, and child clubs across three clusters. - The training sessions took place in Phulwari on March 30–31, in Urma on April 1–2, and in Hasuliya on April 3–4. - Participants included representatives from ECGs, mothers' groups, and child clubs, with a total of 85 people attending across the three locations. - The training was facilitated by FAYA Chairperson Sher Bahadur Basnet. - Key topics included rights and basic needs, education vs. literacy, civic and moral education, types of education, and the 10 educational rights. Participants also learned how to use a checklist to collect data from schools and communities. - The first day focused on theoretical learning. On the second day, participants were divided into three groups to visit schools and communities. They gathered information by interviewing headteachers, reviewing school records, and speaking with parents and students using the checklist. - Each group presented their findings, which helped them better understand how to observe and assess their children’s educational environment and how to engage in school monitoring. - The session concluded with a discussion on the importance of taxation for quality education and the role of local resource mobilization. Distributed PRS visibility to schools - PRS visibility boards were distributed to all 30 project schools. - Each board displayed the 10 educational rights to raise awareness among school stakeholders and to enhance the visibility of the project. - The boards featured the logos of NORAD, FAYA, and ActionAid Nepal and served both as a tool for awareness and as an official project marker. - Schools were encouraged to install the notice boards outside classrooms or office areas to share information and promote the 10 rights. - This initiative helps increase awareness among school stakeholders about children’s educational rights and reinforces their presence and importance within the school environment. Follow up support to schools to organize annual social audits Orientation and supports schools to organize annual social audits - As per the Education Act, all schools are required to conduct a social audit between Bhadra and Ashwin and submit the report to the District Education Office (DEO), which then offers incentives based on school performance. - To support schools in properly carrying out the social audit process and ensuring public participation, one-day orientations were conducted in 29 schools with the presence of the respective Resource Persons (RP) from each area. - The orientation sessions included participation from School Management Committee (SMC), Parent-Teacher Association (PTA), Education Concern Group (ECG) members, head teachers, available teachers, and child club members altogether 810 participants, including 480 females and 330 males. - Previously, many schools completed only documentation without following the proper process; however, after the orientation, schools began conducting social audits transparently in the presence of stakeholders. - As a result, school stakeholders are now familiar with the audit process and actively provide feedback on school activities. After this orientation many schools first conducted social audit in process and in the presence of stakeholders. Social Audit flyer Published - A flyer was published in May outlining the process of conducting annual social audits in community schools. - The flyer aimed to raise awareness among school stakeholders about the importance of social audits, the key components covered in the audit report, the steps involved in the process, and how the final report is produced. This initiative was intended to encourage greater community involvement and strengthen local ownership of community schools. - The primary objective of the flyer was to inform stakeholders and encourage their active support, feedback, and shared responsibility in the audit process. Annual Social Audit Orientation conducted - In May, annual social audit orientation sessions were conducted in 24 out of the 30 NORAD project schools. - These orientations aimed to raise awareness and encourage greater involvement of community members in the social audit process. - A total of 711 participants took part in the 24 events, including 286 males and 425 females. - Participants included SMC chairs, PTA chairs, head teachers, child club members, ECG members, and mothers' group representatives from each respective school. - Through the orientation, stakeholders gained a clear understanding of the importance of social audits, the components of the audit report, the steps involved, and how the final report is produced. This knowledge is expected to foster stronger community ownership and engagement in school governance. - As per the Social Audit Guidelines, participants expressed their commitment to supporting their schools in conducting timely social audits and receiving additional incentives from the DEO for promoting quality public education for their children. | June /Dec March 2017 March 2017 May 2017 May 2017 June 2017 | June/Dec March 2017 March 2017 May 2017 May 2017 June 2017 |
| M3 Local coordination and accountability mechanisms created for local education support. | Formation and mobilization of Education Concerned groups (30 groups) - A total of 30 Education Concern Groups (ECGs) were formed with the participation of local community members, educators, and youth. - These groups comprise 175 members in total, including 82 females and 93 males. - ECGs hold monthly meetings where they discuss the learning environment in their respective schools, monitoring activities, and ways to enhance learning both at school and at home. - The ECGs have independently decided to conduct rotational monitoring visits to schools to check on teacher attendance in classrooms and to provide necessary support to schools. They also coordinate with local authorities and DEO personnel to improve the learning environment. Conducted Capacity Building Training to ECG members on tax power - A two-day Tax Power Campaign training was conducted for Education Concern Group (ECG) members at Nayaram Hotel, Dhangadhi, to enhance their capacity. - The training aimed to increase the ECG members' knowledge about tax-related issues and motivate them to implement similar initiatives at the community level. - A total of 30 ECG members, representing each of the 30 project school areas, participated in the training, which took place on May 30th and 31st. Out of the 30 participants, 7 were male and 23 were female. The main objectives of the training were: - To build capacity on tax power, - To disseminate and raise awareness about taxation, - To educate participants on the different types of taxes, - To promote tax justice, - To empower participants to mobilize citizens on tax justice issues, - To identify the roles of key stakeholders in supporting public quality education, - To localize the tax power campaign at the community level. - As a result of the training, participants developed individual plans for the tax power campaign, which will involve SMC, PTA, teachers, and parents. These plans aim to inform the community about tax power, tax justice, and their connection to quality education. Formation and mobilization of Education Concerned groups- meetings Regular Meeting of Education Concern Group. - Regular meetings of the Education Concern Group (ECG) were held for each of the 30 groups. - During these meetings, they discussed their children's education, school attendance, and the improvements observed at their schools, emphasizing the importance of continuing these efforts. Many ECG members have now enrolled their children in their respective schools. - They also reflected on the work done last year and the changes that followed the formation of the groups. They agreed that this year, they must collaborate more closely with schools to support various initiatives aimed at providing quality education for their children. - They reviewed their involvement in the enrolment campaign and the progress made. - Plans were made to assist schools in regulating grade-level teaching, which is seen as crucial for delivering quality education, alongside regular monitoring and support. - In Bandevi PS Majhara, Hasuliya, ECG members decided to engage with the contractor of the fishpond and local community members to contribute a portion of the collected funds to the school. - Similarly, in Sarvodaya SS School, Phulwari, ECG members organized a meeting with the fishpond contractor and the community, resulting in some financial support for the school’s educational quality. - In Janjyoti, Urma, ECG members planted bamboo trees around the school, with plans to sell them in the future and use the proceeds for various school-related activities. Formed joint District Project Advisory Committee (D-PAC) - The project document included a provision for a District Project Advisory Committee (DPAC). - As per this provision, a 7-member committee was formed, chaired by the Local Development Officer (LDO), with representatives from the Women and Children Office, District Administration Office, Federation of National Journalists, NGO Federation, District Education Office, and FAYA Nepal. - The committee held two meetings and conducted field visits. During their visits, they observed CCL classes and other school governance-related activities, and they recommended expanding these CCL classes to other schools and VDCs as well. DPAC visit and meeting - As per the project plan, a semi-annual District Project Advisory Committee (DPAC) meeting and visit were conducted in June. - The purpose of the visit was to gather feedback for further improvements in project activities or to revise any activity modalities to achieve the project goals. During the visit, project schools were reviewed, and a meeting was held at the FAYA hall. - The meeting included participation from the School Supervisor, Section Officer of the DDC, Women Development Officer, Chairpersons of the NGO Federation and FNJ, as well as other journalists. They visited three schools across three clusters, interacting with Head Teachers, other teachers, SMC members, PTA, ECG members, and child club representatives. - After engaging with stakeholders and students, they found that parental involvement in schools had increased, student learning achievements had improved, and the overall learning environment had greatly improved. - Following the school visits, a review meeting was held where updates from January to June were shared. Based on the visit, they recommended that the project team plan for the continuation of these initiatives in schools even after the project phase-out. - They highlighted that the CCL process, ECG engagement, and child clubs were significantly supporting the improvement of the learning environment, urging school stakeholders to continue these processes beyond the project phase. - The final DPAC visit, and meeting took place in the presence of the Mayor of Dhangadhi Sub-Metropolitan City and the Chairperson of Kailari Rural Municipality. - During this visit, they inaugurated the newly constructed community libraries and handed them over to the schools for regulation. - Both officials emphasized the need for further improvements and support to the schools and libraries from the local government in necessary areas. | 30 & 31st May 2017 May 2017 June 2017 | 30 & 31st May 2017 May 2017 June 2017 |
| M4 Empowerment of local groups especially children’s groups, to take a strong role in school governance and funding for improvements in local school quality and access, including retention of girls in education | Updating school improvement plan(SIP) - An orientation on the SIP update process was conducted in 15 schools, with a total of 506 participants, including 247 females and 259 males. - Following the orientation and discussions, the schools recognized the importance of updating the SIP and committed to doing so regularly each year. - After the orientation, all 30 project schools updated their SIPs and submitted them to the resource center. - A notable achievement was that two schools from our project, Garima PS and Shankar PS in Hasuliya, created and submitted their SIPs to the resource center for the first time. - In their SIPs, these schools included key findings from the CER report, such as conducting timely social audits, properly managing available resources (e.g., toilet cleaning), and holding meetings with parents regarding student progress. supports schools to update SIP - According to government guidelines, community schools are required to create a School Improvement Plan (SIP) for a five-year period, which must be updated annually. - While schools have various plans for the five-year period, each year they need to remove the items that have been achieved and revise the plan to address areas that still need attention. - This process involves meetings and discussions with the SMC, PTA, teachers, and students, with the Head Teacher (HT) taking the lead responsibility. - After these discussions, the SIP will be updated and rewritten in the necessary areas. Once printed, it must be submitted to the District Education Office (DEO) by Shrawan, so the DEO can release the fourth-quarter salary for teachers. - Following these discussions, the stakeholders expressed satisfaction and agreed to update the SIP every year as required. - All 30 schools in the project have now updated and submitted their SIPs to the Resource Centre. Notably, Garima PS and Shankar PS in Hasuliya created and submitted their SIPs for the first time, thanks to the orientation and support provided. - All 30 project schools have successfully updated their SIPs. SIP Flyer Published - As per the SIP guidelines, each school is required to develop a five-year School Improvement Plan and update it annually. - To raise awareness among school stakeholders, key messages regarding the process, importance, objectives, benefits, and the necessary components of the SIP were gathered for the publication of an SIP flyer. This draft was shared with AAN before being finalized and published. - The flyer is designed to increase the knowledge of school stakeholders and guide schools in updating their plans accurately. - The primary goal of publishing this flyer is to enhance stakeholders' understanding and encourage their input during the SIP preparation process. SIP process Orientation - A School Improvement Plan (SIP) orientation was conducted for 24 project schools—10 in Phulwari, 8 in Hasuliya, and 6 in Urma. - As per government guidelines, all community schools must update their SIP and submit it to the resource centre by July. Based on these submissions, the District Education Office (DEO) allocates various incentives. - The orientation sessions were attended by Head Teachers (HTs), School Management Committee (SMC) Chairs, Parent-Teacher Association (PTA) members, child club representatives, and Education Concern Group (ECG) members from the respective schools. - Across the 24 orientations, a total of 812 participants took part 381 males and 431 females. - The participating stakeholders gained awareness about the SIP process. After attending the sessions, many expressed their commitment to supporting schools in developing and implementing effective plans that enhance the learning environment and contribute to the overall quality of public education. Orientation on government provisions to promote girls’ education and establish mechanisms to promote girls education at school level Conducted Orientation on Girls education Government Provisions - We have conducted Girls Education Government provisions orientation to school stakeholders last year in 2016 there oriented 25 school stakeholders out of 30 project schools and in 2017 there oriented 5 remaining school stakeholders. - So, we have planned in APB to orient remaining 5 school stakeholders this year. - So, for that we coordinate with DEO and Resource Person for facilitation the orientation. - In that orientation there was participation of SMC, PTA, HT, Child club, ECG and conducted in kalimai LSS, Janata LSS and Janata PS where there was participation of 68 females and 39 males altogether 107 persons in three schools of Hasuliya VDC. - That orientation was facilitated by RP of Hasuliya resource centre and main topics were girl’s scholarship provisions, textbook and dress support, female teacher, girls’ friendly toilets, females reserved seats in different committees, different other government programs enhance capacity building of girls and females. - After knowing such provision participant stakeholders thanked us for sharing such things that many of them, they never heard before and suggested for conduct such activities in different times in different other committees and meetings also. - They also said that afterward we will see and ensure such facilities and participation of girls and females in different activities. Formation and Strengthening Girls Education Network (GEN) at district level - A meeting for the formation and strengthening of the Gender Equality Network (GEN) was held at the District Education Office (DEO) in Kailali, chaired by the DEO. - The meeting was attended by representatives from the DEO, School Inspector, Women and Children Development Office (WCDO), District Child Welfare Committee, Dalit Rights Forum, Mercy Corps, World Vision, and other organizations. - The main agenda included clarifying the roles and responsibilities of GEN members, discussing the need for a Gender Focal Teacher in every school, and agreeing that the committee would proactively respond to any issues related to women and girls. - It was decided that regular GEN meetings would be held to address and share updates on gender-related concerns. - One key outcome of the meeting was the establishment of a Gender Focal Person in each school. As a result, 25 Gender Focal Persons were appointed across 25 project schools. - These focal people will coordinate with GEN members to address issues affecting girls and ensure that their concerns are heard and acted upon. Conducted Girls Education Government Provisions Interaction - Girls' Education Government Provisions Interaction programs were conducted in 30 project schools, with the participation of Education Concern Groups (ECGs), Mothers’ Groups, and girl students. - A total of 932 individuals took part in these interactions, including 105 males and 827 females. - The events were held from mid-March through the end of the month. - Discussions focused on existing government provisions aimed at supporting girls' education, emphasizing their importance in helping retain girls in school and improving their academic performance. - Participants also explored the challenges faced by girls in their communities and how mothers can play a supportive role in their education. - Mothers expressed their commitment to monitoring whether the government-provided facilities are available in their local schools and pledged to support the schools from their communities. Formation and Strengthening Girls Education Network (GEN) at district level Coordinated for Gender Focal Person. - Girls' Education Government Provisions Interaction programs were conducted in 30 project schools, with the participation of Education Concern Groups (ECGs), Mothers’ Groups, and girl students. - A total of 932 individuals took part in these interactions, including 105 males and 827 females. - The events were held from mid-March through the end of the month. - Discussions focused on existing government provisions aimed at supporting girls' education, emphasizing their importance in helping retain girls in school and improving their academic performance. - Participants also explored the challenges faced by girls in their communities and how mothers can play a supportive role in their education. - Mothers expressed their commitment to monitoring whether the government-provided facilities are available in their local schools and pledged to support the schools from their communities. Child club leads extracurricular activities Reformation of Child clubs and extracurricular activities - With the start of the new academic session in May, some students transferred to other schools, leading to the reformation of child clubs in 14 out of 15 project schools. - A total of 147 students participated in the reformed child clubs: 14 students from 2 schools in Hasuliya, 45 from 5 schools in Urma, and 88 from 8 schools in Phulwari. - During the reformation meetings, committee members were oriented on the project’s objectives, the previous activities of the child clubs, and their annual action plans. - In the past, students were often hesitant to join child clubs. However, this year saw increased interest and enthusiasm, making it more challenging to form the clubs due to high demand. With the support of focal teachers and Head Teachers, the clubs were successfully reformed. - Notably, there was a significant rise in the participation of girls currently, 70% of child club members are girls, while 30% are boys. - As per the previously developed action plans, extracurricular activities were conducted in all 15 project schools. Developed Annual Action Plan of Child Clubs - Monthly child club meetings were conducted in all 15 child clubs during the reporting month. - The primary agenda of these meetings was to develop the annual action plans for each child club, ensuring a structured approach to implementing various activities throughout the year. - An action plan format was shared in collaboration with the focal teachers, and with their support, all 15 child clubs successfully prepared their annual action plans. - The plans included a range of student-led activities supported by focal teachers and ERAs. Most activities were scheduled according to seasonal relevance and appropriateness, including enrollment campaigns, school premises cleaning, and celebrations such as Children’s Day. Establishment of community library in school premises Constructed Community Library at School Premises: - A library construction concept was developed, which included 20 indicators to guide the selection of schools. - Out of the 30 project schools, only 3 were to receive library support one in each cluster. A selection committee was formed based on the concept and tasked with reviewing the collected information and recommending suitable schools. - Information was gathered from all 30 schools using a standardized form, and a meeting was held with the designated committee members to review and finalize the selections. - Based on the committee’s recommendations, three schools were selected: Jana Sewa Primary School in Hasuliya, Sarvodaya Secondary School in Phulwari, and Rastriya Lower Secondary School in Urma. - Following the selection, a site visit was conducted by the FAYA Chairperson, Policy and Partnership Coordinator Dhanpati Dhungel, Program Coordinator Mukesh Pant, and respective field staff to assess the available spaces for library setup. - They inspected the rooms proposed for renovation and discussed plans with Head Teachers and school staff. - Each school’s School Management Committee (SMC) then formed a construction and management sub-committee, chaired by an SMC member, to oversee the library setup. - Formal agreements were signed with the schools, and renovation work was initiated. Although there were delays due to the election period, all three libraries have now been successfully completed. - The libraries have been officially handed over to the schools for ongoing use and management. - Currently, both students and community members are visiting the libraries during their free time, making active use of the new facilities. Conducted Enrollment Campaigning - Enrolment campaigns were conducted in coordination with school stakeholders to support the national enrolment drive. - The government declared an official enrolment campaign from 2nd to 14th Baishakh, during which schools were required to actively promote student enrolment. - In support of this initiative, project teams organized and participated in enrolment campaigns from April 16th to 28th, 2017, across all project schools. Banners were prepared for each school to raise awareness and visibility. - The campaign involved ECG members, teachers, child club representatives, SMC/PTA members, and other local stakeholders who conducted door-to-door visits. - During these visits, they inquired about school-aged children in each household and encouraged parents to enrol any out-of-school children, emphasizing the importance of education and the risks of repeating past hardships. - Parents were informed about the various government-provided facilities available in community schools and were encouraged to take advantage of them. - As a result of the campaign, enrollment numbers significantly increased. In Urma, 4 students transferred from private to community schools. New Kalika Primary School saw an increase of 56 students, Sarvodaya Secondary School in Phulwari enrolled 34 new students (16 from private schools), Shivaganga LSS added 26 (10 from private schools), and Jana Kalyan PS recorded 38 new enrollments (5 from private schools). Several other schools also reported increased student numbers. | June 2017 June 2017 February 2017 March 2017 February 2017 February 2017 May 2017 January 2017 April 2017 | June 2017 June 2017 February 2017 March 2017 February 2017 February 2017 May 2017 January 2017 April 2017 |
| M5 Local level advocacy to improve quality and funding for education through fair tax Malawi, Mozambique, Tanzania and Nepal | A Policy brief on ‘Taxation and investment on public education at local level’ Local level activista mobilization for tax power campaigning - An activist’s formation and orientation meeting was conducted at FAYA Nepal with the participation of enthusiastic youth interested in advocacy and civic engagement. - A total of 38 youths attended the meeting, resulting in the formation of a 37-member activists’ group, consisting of 22 girls and 15 boys. - The session was facilitated by FAYA Chairperson Sher Bahadur Basnet and Board Member Birendra Chaudhary, who guided the youth through the orientation. - As part of their engagement, the activists developed an action plan for the "Tax Power" campaign, including a photo action and a signature collection campaign in Dhangadhi. - Two major campaign events were successfully organized as part of this initiative. - Through these events, the activists were able to directly reach around 2,000 individuals and indirectly reached an additional 500 people via local radio and television broadcasts. - The campaign received coverage in four local newspapers, helping extend its visibility and impact. - The core objective was to raise awareness among citizens about the importance of taxes, why they are paid, and how tax revenues contribute to public services like quality education and infrastructure development. - The campaign helped foster a sense of accountability and encouraged people to monitor how tax money is being utilized. - Tax-related messages were also integrated into other district and local-level project activities to reinforce awareness around tax justice. - As a result, there is a noticeable increase in public discourse and awareness around taxation and civic responsibility. |  |  |
| Output 2 Strong national coalitions, teacher unions and well-informed civil society movements hold governments to account for progressive tax reforms that will lead to increased spending on public education both to increase access and improve quality. |  |  |  |
| Milestone | Activity report (including any deviations from original plan by 3 months or more) | Planned completion date | Actual completion date |
| M6 National level research on fair tax revenue for quality public education Malawi, Mozambique, Tanzania and Nepal. | Research on ‘Tax Generation, Exemption and its impact on Public Education Financing’ Conducted Tax Power interaction with local leaders: - A "Tax Power" interaction program was organized with local leaders from all 13 local governments in Kailali district. The event was attended by Mayors and Deputy Mayors, along with other key stakeholders. - A total of 61 participants (23 females and 38 males) were present, including local representatives, educators, journalists, professors, lawyers, and officials from various district-level agencies. - The objective of the interaction was to discuss tax allocation and utilization mechanisms, with a focus on increasing investments in the education sector. - The session was facilitated by FAYA Project Coordinator Mukesh Pant, while Policy and Partnership Coordinator Dhanpati Dhungel presented a paper on tax distribution and the share of the national budget allocated to education. - The presentation highlighted key challenges, such as the limited budget allocation to education and the inefficient utilization of the funds that are allocated, especially concerning learning outcomes. - The event spurred an in-depth discussion among participants on how to ensure proper use of available resources. - The Mayor of Ghodaghodi Municipality shared that Rs. 3 crore 22 lakhs had been allocated for education, with school mapping already underway to assess students, teachers, infrastructure, and more. - The Chairperson of Kailari Rural Municipality noted an allocation of Rs. 80,000, which will be invested in areas identified as priorities following school mapping. - Several other local leaders also expressed their commitment to developing localized education policies, identifying relevant resources, and implementing a one-door system for effective service delivery and improved educational outcomes. Support national coalitions to organize empirical research, informed by citizen education reports (evidence-based advocacy) | 28th Dec 2017 | 28th Dec 2017 |
| M7 Production of public materials to engage widespread citizen support | IEC Materials to raise awareness on ‘taxation and levels of government spending on education’ Occasional publications for shared learning and policy influencing (Case studies/change stories; Information Education Communication Materials; Fact Sheets; Tool Kits) |  |  |
| M8 Mass citizen engagements to demonstrate widespread support and hold governments accountable | Celebrated Global Action Week of Education (GAWE) From April 23 to 29, FAYA Nepal joined the global community in celebrating Global Action Week for Education (GAWE), an international campaign that promotes the right to quality education. Various educational organizations across Nepal marked the week with diverse activities, and FAYA celebrated GAWE through cluster-level programs across its working areas. April 24 – Urma Cluster - Activities were conducted at Jana Kalyan Primary School, Jalghusra, Urma. - 89 participants attended (54 females, 35 males), including students and teachers from all 10 schools in the cluster. - Speech Competition: 5 Lower Secondary School (LSS) students (3 girls, 2 boys) spoke on the theme “Tax Power for Quality Education.” - Drawing Competition: 9 Primary School (PS) students (5 girls, 4 boys) illustrated their vision of a "Model School." April 25 – Phulwari Cluster - Event hosted at Phulwari LSS with participation from all 10 schools, teachers, students, and parents. - Total attendance: 80 (53 females, 27 males). - Speech Competition: 8 students (6 girls, 2 boys) shared perspectives on "Tax Power in Quality Education." April 26 – Hasuliya Cluster - A gathering of 60 stakeholders (41 females, 19 males). - Drawing Competition featured 18 students (12 girls, 6 boys) from 10 schools drawing their idea of a model school. - Street Drama (April 24–26) - Performed in all three clusters with an estimated 200 viewers (115 females, 85 males). - Themes included quality education, education rights (10 rights), and tax power. April 27 – Signature Campaign - Conducted across all 3 clusters to raise awareness on tax and education rights. - Key messages: “Quality education is every student's right. Taxes fund better education.” Participation: - Urma: 250 signatories (128 males, 122 females) - Hasuliya: 318 signatories (188 males, 130 females) - Phulwari: 378 signatories (225 males, 153 females) Radio Program on Tax & Education - A special radio discussion was broadcast through Dinesh FM Dhangadhi using the Sajha Manch model. - 13 panellists participated, including: - 3 representatives from the Teachers' Union - SMC Network representatives - Candidates from the 3 major political parties - Officials from the District Education Office and Tax Office - Members from the Consumer Rights Protection Forum - A local journalist The campaign effectively raised public awareness on the importance of taxes in improving education quality and emphasized citizen responsibility and government accountability in educational investment. | 23 to 29 April 2017 | 23 to 29 April 2017 |
| M9 Media work to drive the public and political debate on funding quality public education through fair tax | Engage Media Campaign on Impact of ‘tax exemption and investment on education’‘ Documentation & Learning-Video documentation |  |  |
| M10 National movement building between education and tax justice civil society, and participation in key influencing moments | Annual Public Education Conference FAYA Nepal has actively engaged with the Gender Equity Network (GEN) to mobilize civil society organizations (CSOs) in advocating for progressive taxation and equitable investment in girls' education. As part of this initiative, a National Workshop on Taxation and Government Spending on Education was organized to raise awareness and build momentum around the need for fair and adequate public financing in the education sector. Additionally, efforts have been made to strengthen national coalitions and civil society movements to facilitate public discourse at both regional and national levels, focusing on the progressive realization of the right to education. These initiatives aim to ensure that education financing policies are inclusive, equitable, and responsive to the needs of marginalized groups, especially girls. |  |  |
| M11 National level advocacy with decision-makers to hold governments accountable | FAYA Nepal engaged in strategic lobbying and advocacy efforts aimed at holding the government accountable for its commitments to quality public education. The activity focused on influencing national-level policy dialogue and decision-making processes by advocating for increased domestic resource mobilization, particularly through progressive taxation, to ensure sustainable and equitable investment in education. By engaging with parliamentarians, government officials, and relevant stakeholders, the initiative promoted transparency, accountability, and the prioritization of education in national budgeting and planning processes. These efforts aimed to amplify the voices of marginalized communities, especially girls and disadvantaged groups, and pushed for policy reforms to guarantee quality, inclusive, and accessible education for all. |  |  |
| # Output 3 International education and tax justice networks consolidate a global movement to advocate for improved progressive tax reforms that contribute towards the realization of the right to education for all children. |  |  |  |
| Milestone | Activity report (including any deviations from original plan by 3 months or more) | Planned completion date | Actual completion date |
| M12 International review workshops and for sharing experiences and lessons learned |  |  |  |
| M13 Research and publications |  |  |  |
| M14 Solidarity campaigning at international level |  |  |  |
| M15 Alliance building and advocacy |  |  |  |

## 3. Progress against indicators (2-3 pages)

| Using the table below, please provide a summary of progress against each output, with reference to each output indicator. Please refer to targets against each indicator as outlined in the project Goal Hierarchy. Please follow the definitions below when populating your red, amber, green (RAG) status per output. You should also include details on any constraints to the progress of delivery against your log-frame targets (and how these may be overcome over a given time period). Please specifically highlight any potential delays of 3 months or more to specific activities. RAG definitions: Red: Behind schedule to deliver output to agreed specification, timeframes and/or budget and no mitigating actions have been put in place, or are not possible in this circumstance. Amber: Behind schedule to deliver output to agreed specification, timeframes and/or budget but mitigating actions have been put in place to rectify the issue. Green: On schedule to deliver output to agreed specification, timeframes and budget. |  |  |
| --- | --- | --- |
| Output 1 Children, especially girls, parents, community members and local civil society have a strong role in ensuring that local education services are of high quality, increase access for girls and are adequately funded by government through fair taxation. |  |  |
| Output Indicator | RAG status | Update on progress |
| 1.1. % of schools with active community representation in school governance incl. monitoring school budgets/expenditure and education rights | Revised Y3 Targets: Nepal: 80% | In Kailali 30 out of 30 target schools have active community representation in school governance. Education Concern Groups (ECGs) have been meeting regularly in schools. - ECG members held regular meetings to review and reflect on their activities during the reporting period. They conducted rotational visits to schools, taking turns to monitor whether classes were running smoothly, if teachers were arriving on time, and to engage in discussions about students’ learning achievements and the types of support required. - In Samaiji Primary School, Urma, the Head Teacher was not attending school regularly and often left early when he did. Following consistent monitoring and objections raised by ECG members, the Head Teacher has now begun staying for the full school day. - ECG members from Sarvodaya Secondary School in Phulwari decided to organize integrated meetings involving SMC, PTA, teachers, students, and mothers' groups to collectively discuss and address school-related contextual issues. - Recently, mothers' group members have become more actively engaged with schools. They have been visiting to observe the school environment and participate in various school activities such as tree planting and cleaning campaigns. |
| 1.2. # of local actions that advocate for improved quality/financing of education | Revised Y3 Targets: Nepal: 5 | In Kailali, many local actions have been carried out in the period of Jan to Dec of Year 3 including: - A two-day Tax Power training was organized for ECG members to strengthen their understanding and capacity on tax justice issues. Following the training, ECG members developed local action plans to initiate community-based awareness activities on tax power in their respective areas. - Bhim Tiruwa, an ECG member from Garima Primary School in Hasuliya, actively participated in multiple Tax Power trainings and orientations. Leveraging his learning, he initiated local awareness activities related to tax power within project interventions. Notably, during the FPAN-led reproductive health orientation sessions in eight secondary schools in Hasuliya, Bhim Tiruwa facilitated one of the sessions, integrating the concept of tax power into the orientation. - A refresher training on Child-Centred Learning (CCL) was conducted for previously trained teachers. The session focused on clarifying challenging tools, reviewing implementation progress, assessing observed changes, and addressing difficulties faced during application. - Orientation and training on the Participatory Rights Scorecard (PRS) were carried out to help relevant stakeholders understand the 10 rights related to education, identify existing gaps, and determine areas where further improvement was needed. - Awareness sessions on government provisions for girls’ education were conducted to inform community members and stakeholders about the available support mechanisms aimed at improving girls’ retention and learning outcomes in schools. - Tax Power campaigns were launched across all 30 project school areas by ECG members. Various activities such as interactive programs, orientations, and rallies were organized within school catchment areas to raise community awareness about the importance of tax and its connection to quality education. |
| 1.3. # of actions per target area to increase attendance and retention of girls in school | Revised Y3 Targets: Nepal: 4 | In Kailali, local actions have been carried out in the period of Jan to Dec of Year 3 including: - Regular meetings of the Education Concern Group (ECG) were held to discuss the issue of school dropouts and strategies to reintegrate them. At Janjyoti Primary School in Urma, ECG members, in collaboration with the child club, successfully convinced and re-enrolled two girls back into school this year. - Following directives from the District Education Office (DEO), Gender Focal Teachers were appointed in every school. These teachers are responsible for addressing girls' issues at the school level. If an issue cannot be resolved at the school, it is referred to the District Committee for further action. - Orientation sessions were conducted on government provisions for girls’ education to inform and encourage girls to stay in school by helping them and their families understand the available support. - Child clubs were also mobilized to support school re-enrolment efforts. They played an active role in motivating dropout girls by highlighting the importance of education and the long-term challenges they might face without it. |
| 1.4. % increase in local authority funds provided for schools for rights-based school improvements | Revised Y3 Targets: Nepal: 20 | In Kailali, 7 school out of 30 school have provided funds by the local authorities and communities. - In Hasuliya, following participation in the participatory planning process, several schools received financial support: Garima Primary School received NPR 50,000 for electricity and boundary wall construction, Shankar Primary School received NPR 50,000, Jana Sewa Primary School received NPR 40,000, and Janata Primary School received NPR 50,000. - At Shankar Saraswoti Basic School in Phulwari, ECG Coordinator Tulsi Ram Upadhyaya established a revolving fund of NPR 51,000 to provide scholarships for students. - In both Sarvodaya Secondary School of Phulwari and Bandevi Primary School in Hasuliya, ECG and mothers’ groups conducted local lobbying efforts and successfully raised additional funds from the community to support school needs. - Additionally, in Hasuliya, temporary teachers submitted a declaration, and as a result, Kailari Rural Municipality committed to allocate approximately NPR 8.5 million towards improving learning achievements. |
| 1. 5. Increased understanding by local communities on issues of fair tax, government revenues and links to education financing | Revised Y3 Targets: Nepal: 50% | In Kailali 265 were participated in the training, orientation, workshop, awareness rising activities on tax power and education issues. Among 65% people showed a basic understanding of tax and education issues: - In Kailali, a total of 154 individuals (118 females and 147 males) from SMCs, PTAs, ECGs, Child Clubs, and Mothers’ Groups participated in orientations on Participatory Review and Scorecard (PRS), CCL refresher sessions, and other related meetings and orientations. - At Jana Jagriti Primary School in Urma, Child Club members performed a drama on tax power as part of their extracurricular activities. The students creatively portrayed roles such as a minister, businessman, and teacher, using real-life examples to explain concepts such as what tax is, how it is collected, how it is distributed, and the idea of progressive taxation greatly enhancing audience understanding of tax issues. |

## 4. Lessons learned and recommendations

## Regular attendance of students, teachers, and parental involvement increased following various orientations, interactions, and meetings.

## The community now views the school as their own, understanding that they must coordinate and manage it to create a better learning environment.

## Following orientations, discussions, and meetings, the school has started conducting social audits as per the guidelines, adhering to the prescribed processes.

## ECG members and Mothers’ Groups have regularly visited schools, assisting in cleaning the premises and supporting the school in resource collection to ensure its continued operation.

## It has been observed that involving DEO personnel in coordination with schools enhances effectiveness, as school stakeholders tend to trust DEO staff more than others.

## After attending various tax power training sessions and orientations, community members are now discussing tax issues at the local level, with ECG members also conducting orientations in schools and community meetings.

## Since the implementation of CCL training and grade-specific teaching, students now attend school regularly and maintain a neat appearance.

## Child club members actively share ideas on how to encourage dropout students to return to school.

## With the establishment of child clubs and their active involvement in school activities, teachers and parents have noticed improvements in student participation, communication skills, self-presentation, and more.

## The involvement of parents, ECG members, and Mothers’ Groups in school activities has contributed to a more punctual school environment. Teachers and students now arrive on time, students’ academic performance is improving, and there is greater collaboration between parents and teachers.

## ECG members have realized that continuous engagement in the school environment ensures the quality learning of students, and they are committed to providing ongoing support.

## After implementing CCL classes, more students from private schools are attending community schools, leading to an increase in student numbers compared to the previous year.

## ECG members, such as Bhim Tiruwa in Hasuliya and Bishnu Devi Khadka in Phulwari, are spreading awareness about tax-related issues within their communities.

## After attending school, ECG coordinator of Samaiji PS suggested to the SMC chair that they should hire a qualified English teacher. If there are no funds available, he volunteered to teach without compensation.

## Local communities have become more aware of tax issues and now pay close attention to whether government officials are providing services effectively and whether development budgets are being used properly in their areas, as all of this is funded by the taxes they pay.

## At Jana Sewa PS, during an SMC meeting, ECG members highlighted that instead of investing more money in infrastructure, they should focus on acquiring learning materials and other resources that enhance student achievement.

## Students’ skills have improved in terms of participation in various activities, sharing their opinions, chairing programs, and delivering speeches in front of large audiences.

## The Continuous Assessment system is now being used to evaluate student behaviour, learning, and knowledge.

## Mass sensitization about tax issues has gained momentum at the community level, as meetings have fostered discussions about how tax funds are used, what they fund, and the importance of tax contributions.

## Management and Coordination

## FAYA Chairperson Sher Bahadur Basnet supported in Annual social audit flyer publication. He helped in gathering information’s and instructed staffs on orientation process so that orientation will influence and aware stakeholders deeply. So, that they will support in the social audit process of their respective schools.

## Conducted quarterly DPAC meeting and visit to the project schools. After visiting and participating in meeting s DPAC members suggested of sustainability of ongoing tasks after the project end. They said after this project also those Education concern groups present in school regular basis; those child clubs should also continue to regulate that performance of the children’s. So, project should make some plans for school and share with school.

## In monthly staff meetings FAYA senior management team also join and recommend and suggest for better implementation and they suggest in planned activities for its smoothly conducting.

## If there conducted district level or field level activities, there was participation of FAYA senior team or Chairperson himself so that stakeholders also concentrate on the matter of event and DEO personnel also helped in field level activities for its effectiveness.

## 7. Plans for Next Quarter

The following are the plans for the next quarter:

## 8. Risk Matrix Update

Please give brief details of how ActionAid has handled the relevant risks identified in the proposal (section 6.2) during this reporting period

| Type of Risk | Probability (H,M,L) | Impact on Project H, M, L | Actions Required | By whom |
| --- | --- | --- | --- | --- |
| Project Design and Implementation |  |  |  |  |
| Staff capacity (AA and partners) | M | H | Timely orientation/ refresher on different project issues like tax power and quality education needed to staff of intensive mobilization. | AAN WRC team |
| Project Management and Accountability |  |  |  |  |
| Implementation of National Level Initiatives | M | M | National level initiatives should be implemented in the coordination of required consultants and by sharing information’s to partners. | AAN Focal Person. |
| Donor requirements not fulfilled | H | H | Time to time follow up and need to be updated on ongoing intervention. | Project team. |
| Financial mismanagement by AA and Partners | H | H | Regular coordination and regular financial monitoring should conduct. | AAN Finance team, Audit team. |
| Partnership issues |  |  |  |  |
| Slow implementation by partners | M | H | Support from AAN and DEO personnel, not managed time by DEO personnel and Local election also. | AAN Team, Senior Management, Focal Person |
| External and Political factors |  |  |  |  |
| Elections | M | L | Need to revise plan as government declared for local election because at field level its not possible to conduct activities all stakeholders involved in election. | AAN and Project partner team. |
| Weak tax authorities, corruption of public spending, and low government capacity mean some policy and legislative changes may be realized but additional funds do not reach local schools within this project lifetime. | N/A |  |  |  |
| Research into national financial provision for education and tax policies is likely to threaten certain vested interests, including multi-national corporations benefiting from tax concessions. Information could be blocked or there is a possibility of researchers being threatened, including with legal action. | N/A |  |  |  |
| Government resistance to demands from NGOs to change tax system. | N/A |  |  |  |
| Awareness raising on education rights and financing could raise demands at community level for tangible 'deliverables' such as infrastructure which are not addressed directly by the project | N/A |  |  |  |
| Conflict | N/A |  |  |  |
| Natural Disaster | N/A |  |  |  |
| Public holidays/festivals | M | M | Project team and AAN team should revise plan as local public holidays and made alternatives. | AAN and Partner team. |

## 9. Sustainability (1/2 page)

## The project has focused on tax issues alongside promoting quality education, integrating discussions about tax power in all our activities such as orientations, trainings, meetings, and gatherings. We have also formed Education Concern Groups (ECGs) to increase parental involvement in schools. These groups have actively participated in various project activities, and capacity-building training has been conducted to raise awareness about tax issues. Now, ECG members independently conduct small local initiatives to spread knowledge about tax issues, and they incorporate tax discussions into other programs as well.

## ECG members and Mothers' Groups have recognized that their active participation in school activities significantly improves the learning environment. They now attend schools on a rotational basis and engage in various school activities.

## Child clubs have played a key role in motivating students. There have been noticeable improvements in students' performance, confidence in presenting themselves in front of large audiences, and participation in extracurricular activities. These changes highlight the importance of forming and continuing such clubs in schools.

## Through various orientations, discussions, and the distribution of ICT materials, stakeholders have become more aware of processes such as social audits, School Improvement Plan (SIP) production, resource allocation and distribution, and learning achievement processes. The implementation of the Continuous Assessment and CCL processes has further strengthened their understanding of these vital practices.

## As for ensuring sustainability, the focus has been on engaging community members, especially parents, and building local capacity, which helps maintain momentum and drive long-term positive changes in the educational environment.

## 10.  Material produced

Please share and attach copies of any material produced under this project, such as photos, video, materials etc. for local and national advocacy and campaigning, reaching out to target groups and similar.

Visibility, Book, Flyer, Leaflet, Bag, Cap, Stiker, Poster, Phamphlet and the materails with FAYA, AAN and NORAD Logo

| Materials produced | Quantity | Who used it? | Message contained in the materials |
| --- | --- | --- | --- |
| SIP Flyer | 5000 piece | School/ School stakeholders | SIP producing process, necessity, subject that it covers, responsibilities and its uses. |
| Annual Social Audit Flyer | 10000 piece | School/ School stakeholders | Social audit objective of conduction,Process, subject that it covers, Steps, Final report preduction. |
| CER Report Published | District report -300 copy, School report -450 copy | Organization, School, school stakeholders, distrct line agencies, other organizations and local bodies |  |
| Diary printed during Girls Education Government provisions orientation | 300 copies | ECG, SMC, PTA, Child club and teachers | 10 rights in school, tax issue messages. |
| T-shirt | 40 | Gender Focal teachers | Complaint hearing messages for childrens |
| Raincoat | 7 | Project Staffs | Projet name and logo |
| T-Shirt (Girls child Conference) | 120 | Participants of conference | Child day slogan and logos |